## Hoja1
TSPi Weekly Status Report - Form WEEK
Name | Gabriel Castillo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 2
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 4
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader
Development Manager
Planning Manager |  |  | 15 | 4 | 2 | 2
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 4 | 2
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 0.7 | 0.3 | 1 | 1
Requerimientos T1 |  |  | 1 | 0 | 1 | 1 | 1
Diseño T1 |  |  | 1.2 | 0 | 0 | 1 | 0
Documentacion T1 |  |  | 0.6 | 1 | -0.4 | 1 | 1
Code T1 |  |  | 7.66 | 1 | 1.332 | 1 | 0.2
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 2.7 | 2.232
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items