## TASK
TSPi Task Planning Template - Form TASK
Name | Oscar Javier Moreno Rey |  |  | Date | 2015-03-25
Team | Umbrella |  |  | Instructor | Luis Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Support Manager | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 1.6021 | 1.6021
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 1.6021 | 3.2041
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 1.9225 | 5.1266
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 0.96123 | 6.0878
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 12.2717 | 18.3595
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 1.9225 | 20.282
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 1.2816 | 21.5636
PLAN | 2 | Planning T2 | 5 | 0.2 | 1 | 68.3 | PAGINAS | 0.2 | 3 | 0.32041 | 21.884
REQ | 2 | Requerimientos T2 | 5 | 0.2 | 1 | 69.3 | PAGINAS | 0.2 | 3 | 0.32041 | 22.2044
DES | 2 | Diseño T2 | 5 | 0.3 | 1.5 | 70.8 | PAGINAS | 0.2 | 3 | 0.48062 | 22.685
DOC | 2 | Documentacion T2 | 5 | 0.2 | 1 | 71.8 | PAGINAS | 0.2 | 3 | 0.32041 | 23.0054
CODE | 2 | Code T2 | 5 | 3.8 | 19 | 90.8 | LOC | 30 | 4 | 6.0878 | 29.0932
T | 2 | Test T2 | 5 | 0.6 | 3 | 93.8 | LOC | 4.14 | 4 | 0.96123 | 30.0545
PM | 2 | PostMortem T2 | 5 | 0.14 | 0.7 | 94.5 | PAGINAS | 0.2 | 4 | 0.22429 | 30.2788
PLAN | 2 | Planning T3 | 5 | 0.2 | 1 | 95.5 | PAGINAS | 0.2 | 4 | 0.32041 | 30.5992
REQ | 2 | Requerimientos T3 | 5 | 0.2 | 1 | 96.5 | PAGINAS | 0.2 | 4 | 0.32041 | 30.9196
DES | 2 | Diseño T3 | 5 | 0.3 | 1.5 | 98 | PAGINAS | 0.2 | 4 | 0.48062 | 31.4002
DOC | 2 | Documentacion T3 | 5 | 0.2 | 1 | 99 | PAGINAS | 0.2 | 4 | 0.32041 | 31.7206
CODE | 2 | Code T3 | 5 | 3.8 | 19 | 118 | LOC | 30 | 5,6 | 6.0878 | 37.8084
T | 2 | Test T3 | 5 | 0.6 | 3 | 121 | LOC | 4.14 | 6 | 0.96123 | 38.7696
PM | 2 | PostMortem T3 | 5 | 0.14 | 0.7 | 121.7 | PAGINAS | 0.2 | 6 | 0.22429 | 38.9939
PLAN | 2 | Planning T4 | 5 | 0.2 | 1 | 122.7 | PAGINAS | 0.2 | 6 | 0.32041 | 39.3143
REQ | 2 | Requerimientos T4 | 5 | 0.2 | 1 | 123.7 | PAGINAS | 0.2 | 6 | 0.32041 | 39.6347
DES | 2 | Diseño T4 | 5 | 0.3 | 1.5 | 125.2 | PAGINAS | 0.2 | 6 | 0.48062 | 40.1153
DOC | 2 | Documentacion T4 | 5 | 0.2 | 1 | 126.2 | PAGINAS | 0.2 | 7 | 0.32041 | 40.4358
CODE | 2 | Code T4 | 5 | 3.8 | 19 | 145.2 | LOC | 30 | 7 | 6.0878 | 46.5236
T | 2 | Test T4 | 5 | 0.6 | 3 | 148.2 | LOC | 4.14 | 7 | 0.96123 | 47.4848
PM | 2 | PostMortem T4 | 5 | 0.14 | 0.7 | 148.9 | PAGINAS | 0.2 | 7 | 0.22429 | 47.7091
PLAN | 3 | Planning T5 | 5 | 0.2 | 1 | 149.9 | PAGINAS | 0.2 | 7 | 0.32041 | 48.0295
REQ | 3 | Requerimientos T5 | 5 | 0.2 | 1 | 150.9 | PAGINAS | 0.2 | 8 | 0.32041 | 48.3499
DES | 3 | Diseño T5 | 5 | 0.3 | 1.5 | 152.4 | PAGINAS | 0.2 | 8 | 0.48062 | 48.8305
DOC | 3 | Documentacion T5 | 5 | 0.2 | 1 | 153.4 | PAGINAS | 0.2 | 8 | 0.32041 | 49.1509
CODE | 3 | Code T5 | 5 | 3.8 | 19 | 172.4 | LOC | 31 | 8 | 6.0878 | 55.2387
T | 3 | Test T5 | 5 | 0.6 | 3 | 175.4 | LOC | 6.66 | 9 | 0.96123 | 56.1999
PM | 3 | PostMortem T5 | 5 | 0.14 | 0.7 | 176.1 | PAGINAS | 0.2 | 9 | 0.22429 | 56.4242
PLAN | 3 | Planning T6 | 5 | 0.2 | 1 | 177.1 | PAGINAS | 0.2 | 9 | 0.32041 | 56.7446
REQ | 3 | Requerimientos T6 | 5 | 0.2 | 1 | 178.1 | PAGINAS | 0.2 | 9 | 0.32041 | 57.065
DES | 3 | Diseño T6 | 5 | 0.3 | 1.5 | 179.6 | PAGINAS | 0.2 | 9 | 0.48062 | 57.5457
DOC | 3 | Documentacion T6 | 5 | 0.2 | 1 | 180.6 | PAGINAS | 0.2 | 9 | 0.32041 | 57.8661
CODE | 3 | Code T6 | 5 | 3.8 | 19 | 199.6 | LOC | 31 | 9 | 6.0878 | 63.9539
T | 3 | Test T6 | 5 | 0.6 | 3 | 202.6 | LOC | 6.66 | 10 | 0.96123 | 64.9151
PM | 3 | PostMortem T6 | 5 | 0.14 | 0.7 | 203.3 | PAGINAS | 0.2 | 10 | 0.22429 | 65.1394
PLAN | 3 | Planning T7 | 5 | 0.2 | 1 | 204.3 | PAGINAS | 0.2 | 10 | 0.32041 | 65.4598
REQ | 3 | Requerimientos T7 | 5 | 0.2 | 1 | 205.3 | PAGINAS | 0.2 | 10 | 0.32041 | 65.7802
DES | 3 | Diseño T7 | 5 | 0.3 | 1.5 | 206.8 | PAGINAS | 0.2 | 10 | 0.48062 | 66.2608
DOC | 3 | Documentacion T7 | 5 | 0.2 | 1 | 207.8 | PAGINAS | 0.2 | 10 | 0.32041 | 66.5812
CODE | 3 | Code T7 | 5 | 3.8 | 19 | 226.8 | LOC | 31 | 11 | 6.0878 | 72.669
T | 3 | Test T7 | 5 | 0.6 | 3 | 229.8 | LOC | 6.66 | 11 | 0.96123 | 73.6302
PM | 3 | PostMortem T7 | 5 | 0.14 | 0.7 | 230.5 | PAGINAS | 0.2 | 11 | 0.22429 | 73.8545
PLAN | 3 | Planning T8 | 5 | 0.2 | 1 | 231.5 | PAGINAS | 0.2 | 11 | 0.32041 | 74.1749
REQ | 3 | Requerimientos T8 | 5 | 0.2 | 1 | 232.5 | PAGINAS | 0.2 | 11 | 0.32041 | 74.4954
DES | 3 | Diseño T8 | 5 | 0.3 | 1.5 | 234 | PAGINAS | 0.2 | 11 | 0.48062 | 74.976
DOC | 3 | Documentacion T8 | 5 | 0.2 | 1 | 235 | PAGINAS | 0.2 | 11 | 0.32041 | 75.2964
CODE | 3 | Code T8 | 5 | 3.8 | 19 | 254 | LOC | 31 | 12 | 6.0878 | 81.3842
T | 3 | Test T8 | 5 | 0.6 | 3 | 257 | LOC | 6.66 | 12 | 0.96123 | 82.3454
PM | 3 | PostMortem T8 | 5 | 0.14 | 0.7 | 257.7 | PAGINAS | 0.2 | 12 | 0.22429 | 82.5697
PLAN | 3 | Planning T9 | 5 | 0.2 | 1 | 258.7 | PAGINAS | 0.2 | 12 | 0.32041 | 82.8901
REQ | 3 | Requerimientos T9 | 5 | 0.2 | 1 | 259.7 | PAGINAS | 0.2 | 12 | 0.32041 | 83.2105
DES | 3 | Diseño T9 | 5 | 0.3 | 1.5 | 261.2 | PAGINAS | 0.2 | 12 | 0.48062 | 83.6911
DOC | 3 | Documentacion T9 | 5 | 0.2 | 1 | 262.2 | PAGINAS | 0.2 | 12 | 0.32041 | 84.0115
CODE | 3 | Code T9 | 5 | 3.8 | 19 | 281.2 | LOC | 31 | 12 | 6.0878 | 90.0993
T | 3 | Test T9 | 5 | 0.6 | 3 | 284.2 | LOC | 6.66 | 12 | 0.96123 | 91.0606
PM | 3 | PostMortem T9 | 5 | 0.14 | 0.7 | 284.9 | PAGINAS | 0.2 | 12 | 0.22429 | 91.2848
PLAN | 3 | Planning T10 | 5 | 0.2 | 1 | 285.9 | PAGINAS | 0.2 | 12 | 0.32041 | 91.6053
REQ | 3 | Requerimientos T10 | 5 | 0.2 | 1 | 286.9 | PAGINAS | 0.2 | 12 | 0.32041 | 91.9257
DES | 3 | Diseño T10 | 5 | 0.3 | 1.5 | 288.4 | PAGINAS | 0.2 | 12 | 0.48062 | 92.4063
DOC | 3 | Documentacion T10 | 5 | 0.2 | 1 | 289.4 | PAGINAS | 0.2 | 12 | 0.32041 | 92.7267
CODE | 3 | Code T10 | 5 | 3.8 | 19 | 308.4 | LOC | 31 | 13 | 6.0878 | 98.8145
T | 3 | Test T10 | 5 | 0.6 | 3 | 311.4 | LOC | 6.66 | 13 | 0.96123 | 99.7757
PM | 3 | PostMortem T10 | 5 | 0.14 | 0.7 | 312.1 | PAGINAS | 0.2 | 13 | 0.22429 | 100
|  |  |  | 62.42 | 312.1 |  |  |  |  | 100 | 100
Note on F17: Alvaro Suarez:son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego