## WEEK
TSPi Weekly Status Report - Form WEEK
Name | Oscar Morneo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 4.1
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 4.1 | 0.9 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 4.1 | 0.9
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 0.7 | 0.06 | 1 | 0.2
Requerimientos T1 |  |  | 1 | 0 | 0 | 1 | 0
Diseño T1 |  |  | 1.2 | 0.9 | 0.06 | 1 | 0.2
Documentacion T1 |  |  | 0.6 | 0 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 1 | 1.332 | 1 | 0.2
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 2.6 | 1.452
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## TASK Planning
TSPi Task Planning Template - Form TASK
Name | Oscar Moreno |  |  | Date
Team | Umbrella |  |  | Instructor
Part/Level |  |  |  | Cycle
Task |  |  |  | Plan Hours |  |  | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 5 | 5 | PAGINAS | 0.2 | 1 | 7.4294 | 7.4294 | 0.7 | 0.7 | 1
REQ | 1 | Requerimientos T1 | 5 | 1 | 5 | 10 | PAGINAS | 0.2 | 1 | 7.4294 | 14.8588 | 0 | 0.7 | 1
DES | 1 | Diseño T1 | 5 | 1.2 | 6 | 16 | PAGINAS | 0.2 | 1 | 8.9153 | 23.7741 | 0.9 | 1.6 | 1
DOC | 1 | Documentacion T1 | 5 | 0.6 | 3 | 19 | PAGINAS | 0.2 | 1 | 4.4577 | 28.2318 | 0 | 1.6 | 1
CODE | 1 | Code T1 | 5 | 7.66 | 38.3 | 57.3 | LOC | 11 | 2,3 | 56.9094 | 85.1412 | 1 | 2.6 | 1
T | 1 | Test T1 | 5 | 1.2 | 6 | 63.3 | LOC | 3 | 3 | 8.9153 | 94.0565 | 0.5 | 3.1 | 1
PM | 1 | PostMortem T1 | 5 | 0.8 | 4 | 67.3 | PAGINAS | 0.2 | 3 | 5.9435 | 100 | 1 | 4.1 | 1
|  |  |  | 13.46 | 67.3 |  |  |  |  | 100 | 100 | 4.1
Note on F17: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego

## LOGT
TSPi Time Recording Log – Form LOGT
Name |  | Oscar Moreno |  |  |  |  | Date |  | 2015-04-04
Team |  | Umbrella |  |  |  |  | Instructor |  | Daniel Benavides
Part/Level | [6 empty] | Cycle |  | 1
Date | Start | Stop | Interruption | Delta | Phase/ | Comp-onent |  | Comments
|  |  | Time | Time | Task
2015-03-18 | 20:00 | 21:00 | 8 | 42 | Plan
2015-03-21 | 20:00 | 21:14 | 20 | 54 | Design
2015-04-04 | 21:00 | 22:00 | 0 | 60 | Code
2015-04-04 | 22:00 | 22:42 | 12 | 30 | Test
2015-04-04 | 22:42 | 23:42 | 0 | 60 | Post

## SCHEDULE
TSPi Schedule Planning Template - Form SCHEDULE
Name |  | Oscar Moreno |  |  |  |  | Date |  |  | 2015-03-24
Team |  | Umbrella |  |  |  |  | Instructor |  |  | Daniel Benavides
Part/Level | [6 empty] | Cycle |  |  | 1
|  |  | Plan |  |  | Actual
Week No. | Date |  | Direct Hours | Cumulative Hours | Cumulative Plan Value | Hours |  | Cumulative Hours | Week Earn Value |  | Cumulative Earn Value
1 | 2015-03-28 |  | 5 | 5 | 7.6923
2 | 2015-04-04 |  | 5 | 10 | 15.3846 | 4.1 |  | 4.1 | 1.452 |  | 1.452
3 | 2015-04-11 |  | 5 | 15 | 23.0769
4 | 2015-04-18 |  | 5 | 20 | 30.7692
5 | 2015-04-25 |  | 5 | 25 | 38.4615
6 | 2015-05-02 |  | 5 | 30 | 46.1538
7 | 2015-05-09 |  | 5 | 35 | 53.8462
8 | 2015-05-16 |  | 5 | 40 | 61.5385
9 | 2015-05-23 |  | 5 | 45 | 69.2308
10 | 2015-05-30 |  | 5 | 50 | 76.9231
11 | 2015-06-06 |  | 5 | 55 | 84.6154
12 | 2015-06-13 |  | 5 | 60 | 92.3077
13 | 2015-06-20 |  | 5 | 65 | 100
65