## Week
TSPi Weekly Status Report - Form WEEK
Name | Umbrella | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 25 | 0
Project hours this cycle to date |  |  | 75 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 5 | 3.37 | 0 | 0
Development Manager |  |  | 5 | 5.4667
Planning Manager |  |  | 5 | 6.3167
Quality/Process Manager |  |  | 5 | 8.3
Support Manager |  |  | 5 | 4.1
Totals |  |  | 25 | 0 | 0
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 5 | 7.6 | -2.6 | 1 | 1
Requerimientos T1 |  |  | 5 | 8.1167 | -3.1167 | 1 | 1
Diseño T1 |  |  | 6 | 5.2333 | 0.76667 | 1 | 1
Documentacion T1 |  |  | 3 | 1.4667 | 1.5333 | 1 | 1
Code T1 |  |  | 38.3 | 5.5833 | 13.0867 | 1 | 0.4
Test T1 |  |  | 6 | 0.33333 | 5.6667 | 1 | 1
PostMortem T1 |  |  | 4 | 0.75 | 3.25 | 1 | 1
Totals |  |  | 67.3 | 29.0833 | 18.5867
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items
Note on F27: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego

## Leader
TSPi Weekly Status Report - Form WEEK
Name | Alvaro Suarez | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 3.37
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 3.37 | 1.63 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 3.37 | 1.63
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 0.7 | 0.3 | 1 | 1
Requerimientos T1 |  |  | 1 | 0 | 1 | 1 | 1
Diseño T1 |  |  | 1.2 | 0 | 0 | 1 | 0
Documentacion T1 |  |  | 0.6 | 1 | -0.4 | 1 | 1
Code T1 |  |  | 7.66 | 1 | 1.332 | 1 | 0.2
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 2.7 | 2.232
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Support
TSPi Weekly Status Report - Form WEEK
Name | Oscar Morneo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 4.1
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 4.1 | 0.9 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 4.1 | 0.9
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 0.7 | 0.06 | 1 | 0.2
Requerimientos T1 |  |  | 1 | 0 | 0 | 1 | 0
Diseño T1 |  |  | 1.2 | 0.9 | 0.06 | 1 | 0.2
Documentacion T1 |  |  | 0.6 | 0 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 1 | 1.332 | 1 | 0.2
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 2.6 | 1.452
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Quality
TSPi Weekly Status Report - Form WEEK
Name | Erica Prado | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 8.3
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 8.3 | -3.3 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 8.3 | -3.3
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 2.8667 | -0.37333 | 1 | 0.2
Requerimientos T1 |  |  | 1 | 2.7167 | -0.85833 | 1 | 0.5
Diseño T1 |  |  | 1.2 | 2.25 | -0.21 | 1 | 0.2
Documentacion T1 |  |  | 0.6 | 0.46667 | 0.04 | 1 | 0.3
Code T1 |  |  | 7.66 | 1 | 0 | 1 | 0
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0 | 0 | 1 | 0
Totals |  |  | 13.46 | 9.3 | -1.4017
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Planning
TSPi Weekly Status Report - Form WEEK
Name | Gabriel Castillo | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 6.3167
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 6.3167 | -1.3167 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 6.3167 | -1.3167
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 2.5 | -0.3 | 1 | 0.2
Requerimientos T1 |  |  | 1 | 2.7 | -0.85 | 1 | 0.5
Diseño T1 |  |  | 1.2 | 0.66667 | 0.10667 | 1 | 0.2
Documentacion T1 |  |  | 0.6 | 0 | 0.18 | 1 | 0.3
Code T1 |  |  | 7.66 | 0 | 0 | 1 | 0
Test T1 |  |  | 1.2 | 0 | 0 | 1 | 0
PostMortem T1 |  |  | 0.8 | 0.45 | 0 | 1 | 0
Totals |  |  | 13.46 | 6.3167 | -0.86333
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items

## Development
TSPi Weekly Status Report - Form WEEK
Name | Javier Virviescas | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 42098 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 5 | 5.4667
Project hours this cycle to date |  |  | 15 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 15 | 5.4667 | -0.46667 | 5
Development Manager
Planning Manager
Quality/Process Manager
Support Manager
Totals |  |  | 15 | 5.4667 | -0.46667
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | Percentage
|  |  | Planned | Actual | Value | Week | Completed
Planning T1 |  |  | 1 | 0.83333 | 0.033333 | 1 | 0.2
Requerimientos T1 |  |  | 1 | 0 | 0 | 1 | 0
Diseño T1 |  |  | 1.2 | 1.4167 | -0.043333 | 1 | 0.2
Documentacion T1 |  |  | 0.6 | 0 | 0 | 1 | 0
Code T1 |  |  | 7.66 | 2.5833 | 3.046 | 1 | 0.6
Test T1 |  |  | 1.2 | 0.33333 | 0.26 | 1 | 0.3
PostMortem T1 |  |  | 0.8 | 0.3 | 0.1 | 1 | 0.2
Totals |  |  | 13.46 | 5.4667 | 3.396
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items