## TASK
TSPi Task Planning Template - Form TASK
Name | Umbrella |  |  | Date | 2015-04-04
Team | Umbrella |  |  | Instructor | Daniel Benavides
Part/Level |  |  |  | Cycle | 1
Task |  |  |  | Plan Hours | [6 empty] | Plan Size/Value |  |  |  |  | Actual
Phase | Part | Task Name | # Engineers | Team Leader | Development Manager | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value | Cumulative PV | Hours | Cumulative Hours | Week No.
PLAN | 1 | Planning T1 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 5 | PAGINAS | 1 | 1 | 7.4294 | 7.4294
REQ | 1 | Requerimientos T1 | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 10 | PAGINAS | 1 | 1 | 7.4294 | 14.8588
DES | 1 | Diseño T1 | 5 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 6 | 16 | PAGINAS | 1 | 1 | 8.9153 | 23.7741
DOC | 1 | Documentacion T1 | 5 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 3 | 19 | PAGINAS | 1 | 1 | 4.4577 | 28.2318
CODE | 1 | Code T1 | 5 | 7.66 | 7.66 | 7.66 | 7.66 | 7.66 | 38.3 | 57.3 | LOC | 55 | 2,3 | 56.9094 | 85.1412
T | 1 | Test T1 | 5 | 1.2 | 1.2 | 1.2 | 1.2 | 1.2 | 6 | 63.3 | LOC | 15 | 3 | 8.9153 | 94.0565
PM | 1 | PostMortem T1 | 5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 4 | 67.3 | PAGINAS | 1 | 3 | 5.9435 | 100
|  |  |  | 13.46 | 13.46 | 13.46 | 13.46 | 13.46 | 67.3 |  |  |  |  | 100 | 100
Note on J17: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego