## Hoja1
TSPi Weekly Status Report - Form WEEK
Name | Umbrella | Team | Umbrella |  | Instructor | Daniel Benavides
Date | 2015-04-04 | Cycle No. | 1 |  | Week No. | 1
Weekly Data |  |  | Planned | Actual
Project hours for this week |  |  | 25 | 0
Project hours this cycle to date |  |  | 75 | 0
Earned value for this week |  |  | 0 | 0
Earned value this cycle to date |  |  | 0 | 0
Total hours for the tasks completed this phase to date |  |  | 0 | 0
|  |  | Hours | Hours | Earned | Planned
Team Member Weekly Data |  |  | Planned | Actual | Value | Value
Team Leader |  |  | 5 | 0 | 0 | 0
Development Manager |  |  | 5
Planning Manager |  |  | 5
Quality/Process Manager |  |  | 5
Support Manager |  |  | 5
Totals |  |  | 25 | 0 | 0
Development Tasks Completed |  |  | Hours | Hours | Earned | Planned | PV
|  |  | Planned | Actual | Value | Week
Planning T1 |  |  | 5 |  | 5 | 1 | 7.43
Requerimientos T1 |  |  | 5 |  | 5 | 1 | 7.43
Diseño T1 |  |  | 6 |  | 6 | 1 | 8.92
Documentacion T1 |  |  | 3 |  | 3 | 1 | 4.46
Code T1 |  |  | 38.3 |  | 38.3 | 2,3 | 56.91
Test T1 |  |  | 6 |  | 6 | 3 | 8.92
PostMortem T1 |  |  | 4 |  | 4 | 3 | 5.94
Totals |  |  | 67.3 |  | 67.3
Issue/Risk Tracking
Issue/Risk Name
Other Significant Items
Note on F27: Alvaro Suarez: son 67.3 según el strat en desarrollar el ciclo 1, por tanto agrego